## Sprint Retrospective
Rehearse App — Sprint Retrospective
What Went Well | What Went Poorly | What Ideas Do You Have | How Should We Take Action
The sheet music upload flow now supports PDF, JPEG, document scanning, and unique upload titles, which made the core ingest journey much smoother for real users. | Guest users still hit a hard gate when they try to start upload actions, so some first-time users do not understand why scanning is blocked. | Clarify the guest gate copy so it explains that upload is an account-only feature because files and OCR jobs are stored per user. | Refine the guest upload modal messaging and add a lightweight onboarding hint before the user reaches the blocked action.
The FastAPI conversion backend now validates PDF and JPEG magic bytes, rejects empty or truncated files, and returns authenticated sheet routes instead of leaking public storage URLs. | Queue-capacity and stuck-job recovery are still operationally sensitive areas, especially when Redis load spikes or a worker disappears mid-processing. | Add richer admin-facing visibility for queue depth, recovery events, and recent failed jobs so issues are easier to diagnose. | Instrument queue depth, expose recovery telemetry, and include queue-full plus recovery-loop checks in the regression checklist.
Discover feels much stronger because search, level filters, skill filters, and empty-state handling all map cleanly to the actual song catalog in Supabase. | When filters get very narrow, users can end up with an empty list without enough context about why nothing matched their current combination. | Show more helpful empty-state suggestions such as clearing one chip, changing level, or browsing active songs only. | Update the Discover empty state copy and add a quick clear-filters CTA near the chips row.
The landscape animation screen is in a healthier state: playback controls, tempo sync, backward seek recalculation, and forced orientation handling are all clearly improved in code. | Playback remains one of the most delicate areas because orientation changes, progress syncing, and uploaded JSON rendering all have cross-screen dependencies. | Create a tighter playback smoke suite that covers uploaded sheet data, tempo changes, seek gestures, and proper return to portrait mode. | Formalize an animation-screen test pack and run it on every build touching upload, playback, or sheet rendering.
Profile, daily-goal refresh, onboarding, and password recovery flows now form a more complete user journey with practice tracking, theme selection, and OTP-based recovery. | There are still a few places where onboarding defaults, guest migration, and profile refresh behavior can feel inconsistent if network calls fail. | Reduce silent failure paths and surface clearer retry states around onboarding finalization, profile fetches, and password recovery steps. | Add user-facing retry messaging for profile and onboarding persistence, then back it with targeted UI and service tests.